RA-I WMO Global Campus Meeting 
Action Plan Template

Proposal Title

# Training Needs Assessment form

Overview

A general description of the proposed action that summarizes the key goals and states why it is important to accomplish.

Identify the training needs of the community according to its priorities as basis of the training strategy plan

Proposed Partners and their Roles, including the WMO Secretariat

Primary partners, additional partners desired

WMO , RTCs and NMHS

Expected Outcomes

- The training plan can effectively represent the training needs of the communities in RA I. - Fill the gap between community training needs and training program.

Proposed Steps

- Nov-Dec, 2019 Correction and translation of the questionnaire into French - Jan-Feb, 2020 General appraisal of the questionnaire by WMO - Mar-April Send from WMO to PRs and copy to RTCs - May-June RTCs returns questionnaires, English to Egypt, and French to Niger - July – August Collation and analyses of results - Sep -2020 Analyses form sent to WMO

Resources required (tools, skilled experts, financial, others)

Electronic mailing , translators, reviews Etc.

Key Milestones and Proposed Schedule

Same as proposed Steps