## Slide 1
WIGOS Data Quality Monitoring System (WDQMS)
Demonstration project in RA I
The Plan, Status and First Results
Luis Nunes
WIGOS Project Office

## Slide 2: Outline
Rationale (objectives, participants, timeframe)
Monitoring tools
Incident Management tools/procedures
Phases and their status
  Land surface silent stations
  1) + availability of land surface stations
  1)+2) + accuracy of pressure observations
  1)+2)+3) + radiosonde stations accuracy and availability
First results
Next Steps

## Slide 3: Rationale (1)
  Background:
Outcome of 2nd WIGOS Workshop on Quality Monitoring and Incident Management (Geneva, Switzerland December 2015)
  Goal:
Test the concept of the WIGOS Data Quality Monitoring System (WDQMS) and its major components:
  the monitoring function (QM) for data availability and data quality,
  the analysis and evaluation function (Ev),
  the incident management function (IM)
  Steps:
Planning and preparation of the Demonstration Project in RA I: Jan-May 2016;
Running/testing the QM/Ev/IM functions in operational environment: Jun-Nov 2016;
Assessment via a dedicated Workshop and follow-up actions: December 2016

## Slide 5: Rationale (2)
  Participants:
i) Kenya Meteorological Department (KMD)
- operations pilot centre, providing temporary local resources (human and technical);
ii) Tanzania and possibly other WMO Members (English speaking Countries);
iii) NWP Centres (ECMWF, NCEP, JMA) providing monitoring results in near real time;
- Additionally: EUMETNET
  Governance:
- ICG-WIGOS Task Team on WDQMS providing technical advice and support;
- WIGOS Project Office (WMO Secretariat), providing support to participants and training in OSCAR/Surface;
  Tools to be made available by TT-WDQMS and WMO Secretariat:
  a) an online monitoring information/processing system, with geographic visualization tools
  b) an incident management tracking tool;
  Other tools/resources:
  OSCAR/Surface operational and populated

## Slide 6: Demonstration Project

## Slide 7: Monitoring tools
  WIGOS Quality Monitoring Web-tool:
- 1st prototype developed at WMO Secretariat in collaboration with TT-WDQMS:
- for daily quality monitoring and evaluation
-> http://128.65.196.37/wdqms
  ECWMF Wiki page ‘Demonstration Project’:
  - to identify silent stations
  (missing in the quality reports of ECMWF, NCEP and JMA, referring to a 24-h coverage)
  -> https://software.ecmwf.int/wiki/display/WIGOS/Demonstration+Project
  WMO Quality Monitoring Portal operated by EUMETNET
  - to identify silent stations or stations providing less data than required,
  - and stations showing large accuracy errors of pressure according to ECMWF O-B results
  -> https://eucos.dwd.de/ravi
  OSCAR/Surface
  - to identify (non-)compliance in station metadata information
  -> https://oscar.wmo.int/OSCAR

## Slide 8: Incident Management Tools/Procedures
  Based on a (Google) Website:
- 1st prototype developed at WMO Secretariat in collaboration with TT-WDQMS:
- for raising, communicating and following incidents
-> https://sites.google.com/a/wmo.int/wdqms-demo-ra-i/home
  It contains relevant information about the ‘Demonstration Project’:
  - contacts of people involved,
  - links to the monitoring tools,
  - procedures to be followed by participating countries
  - guidance for the procedures and how to use the website
  - links to each incident ticket
  - repository and summary of incident tickets for each country,
  - everybody involved receives automatic notifications of new tickets created or updates/edits to existing tickets

## Slide 10: Phases
  Phase 1 = Land surface silent stations
  Phase 2 = phase 1 + availability of land surface stations
  Phase 3 = phases 1 & 2 + accuracy of pressure observations
  Phase 4 = phase 1,2 & 3 + radiosonde stations accuracy & availability

## Slide 11: Status of phases 1, 2
  Land surface silent stations and
  Data availability of land surface stations
Total of 32 incident tickets have been raised by KMD:
  21 tickets for KMD stations
    12 tickets have been closed (although 5 are recorded as such in the summary),
    9 tickets have no follow-up;
  11 tickets for TMA stations
    1 ticket has been closed,
    10 tickets have no follow-up
All 32 incidents refer to silent stations or data availability
Inconsistencies between the tickets and the summaries

## Slide 12: Findings from phases 1, 2
Technical problems:
  Editing the website and/or the tickets
Functional problems:
  Initial lack of a national contact for KMD for the follow-up of the incidents, in addition to the person in charge of the monitoring
  (Is there the need for a "System Coordinator"?)
Other problems:
  Update of OSCAR/Surface

## Slide 13: Provisional conclusions
The IM system should create/update automatically the summary(ies) of incidents
Training is essential:
  for the use of a IMS (the Google-site in this case)
  OSCAR/Surface, particularly for National Focal Points
Technical support (IT) is essential to ensure operations of a IMS
The IMS must be robust and based on standard technology and compatible with current HW/SW existing in the market

## Slide 14: Next Steps
Phases 3 and 4 of the Demonstration project will follow:
  Training session for monitoring accuracy of pressure observations: mid September
  Training session for monitoring of radiosonde stations accuracy and availability: mid October
  End of Demonstration project: late November 2016
A TT-WDQMS Meeting/3rd Workshop: December, 13-15 planned
Results to be submitted to ICG-WIGOS: January/February 2017

## Slide 15: Next Steps
The Plan for the WIGOS Pre-Operational Phase:
  (a) Initial WIGOS (land surface stations of the GOS) monitoring capability at ECMWF, NCEP and/or other NWP centres, evaluation and incident management functions by end of 2016;
  (b) Functional specifications and the pilot components developed, following demonstration project: end 2016;
  (c) Full WIGOS (GOS surface-based components) operational QM & IM functionality: end of 2018;
  (d) Monitoring Workshop(s) for JCOMMOPS, GAW, GCOS, GCW and hydrology components of WIGOS: 2016-17;
  (e) Initial monitoring capability for all WIGOS components by end of 2018;
  (f) Mechanisms for routine reporting of monitoring results to EC, regional associations and Members: end 2017;
  (g) Mechanisms and regional structures in place to handle incident management actions and support Members in improving the data availability and quality by 2018 (dependent on establishment of RWCs).

## Slide 16
Thank you
lfnunes@wmo.int
www.wmo.int/wigos