RA-I WMO Global Campus Meeting
**Action Plan Template**

**Proposal Title**

|  |
| --- |
| Training Needs Assessment form  |

**Overview**

***A general description of the proposed action that summarizes the key goals and states why it is important to accomplish.***

|  |
| --- |
| **Identify the training needs of the community according to its priorities as basis of the training strategy plan**  |

**Proposed Partners and their Roles, including the WMO Secretariat**

***Primary partners, additional partners desired***

|  |
| --- |
| **WMO , RTCs and NMHS**  |

**Expected Outcomes**

|  |
| --- |
| * The training plan can effectively represent the training needs of the communities in RA I.
* Fill the gap between community training needs and training program.
 |

**Proposed Steps**

|  |
| --- |
| * Nov-Dec, 2019 Correction and translation of the questioner in French languages
* Jan-Feb, 2020 General appraisal of the questioner by WMO
* Mar-April From WMO to PRs and copy to RTCs
* May-June RTCs returns questioners to Egypt and French to Niger
* July – August Collation and analyses
* Sep -2020 Analyses form sent to WMO
 |

**Resources required (tools, skilled experts, financial, others)**

|  |
| --- |
| Electronic mailing , translators, reviews Etc.  |

**Key Milestones and Proposed Schedule**

|  |
| --- |
| Same as proposed Steps |