## Slide 1
TASKS | ASSIGNED TO | START | END
Preparation of Draft 1 - COMPLETED |  |  | 
Add the draft description of "WMO Voluntary Cooperation Programme" | D/DPO | 17/7/25 | 15/8/25
Add draft description of "Resource Mobilization and Development Activities" | D/DPO | 17/7/25 | 15/8/25
Draft review by EC-CDP for initial feedback | EC-CDP Members | 15/8/25 | 22/8/25
Consolidation of Draft 1 | Coordinated by ETR Office | 22/8/25 | 28/8/25
Draft 1 submitted to TCC-2 (2025) | ETR Office | 29/8/25 | 29/8/25
Presentation of Draft 1 to TCC-2 (2025) | Chair of EC-CDP | 16/9/25 | 16/9/25
Preparation of Draft 2 |  |  | 
Discussions of Draft 1 in EC-CDP-11 | EC-CDP Members | 23/9/2025 | 25/9/2025
Final review and comments by EC-CDP | EC-CDP Members | 25/9/2025 | 17/10/2025
Consolidation of Draft 2 and recommendation by EC-CDP | Coordinated by ETR Office | 17/10/2025 | 30/11/2025
Draft 2 submitted to TCC-1-2026 | ETR Office | 1/12/2025 | 1/12/2025
Presentation of Draft 2 to TCC-1-2026 (for recommendation to EC-80) | Chair of EC-CDP | April/2026 | April/2026
Resolution for approval by EC-80 |  | June/2026 | June/2026
Timeline
Action
Refinement of description of WMO Capacity Development Programme
Completed